## Sprints
Sprint | Goal | Duration | Status | Tasks | Releases | Points
Sprint 1 — Agentic Studio | Turn the CMS into a genuinely agentic, conversational, bilingual platform — build-anything from one chat, governed and on-brand — and ship customer documentation. | 1 week · 9–15 Jun 2026 | Delivered | 29 tasks → | 9 releases → | 121 / 121

## Releases
Release | Date | Commit | Scope | Status | Sprint | Tasks
R1 | 2026-06-14 | aafdcf3 | Agentic core + conversational + live streaming | Released | Sprint 1 → | 6 tasks →
R2 | 2026-06-14 | 5e3b400 | Rich Markdown rendering + website build + recommendations | Released | Sprint 1 → | 2 tasks →
R3 | 2026-06-14 | 3876aed | Intent router + content artifact + publish-to-module | Released | Sprint 1 → | 3 tasks →
R4 | 2026-06-14 | 262e861 | Brand Studio loop + active-brand governance | Released | Sprint 1 → | 2 tasks →
R5 | 2026-06-14 | 7792480 | Design System — prompt-driven theme | Released | Sprint 1 → | 1 task →
R6 | 2026-06-14 | c21fb2b | Build set (video/image/brand/theme) + Claude-like chat UX | Released | Sprint 1 → | 7 tasks →
R6.1 | 2026-06-14 | 249a98d | Brand-guideline palette fix | Released | Sprint 1 → | —
R7 | 2026-06-14 | f734a2a | Cost optimization (Haiku sub-agents) | Released | Sprint 1 → | 1 task →
R8 | 2026-06-15 | 4321000 | Customer collateral docs + build pipeline (PR #1) | Released | Sprint 1 → | 5 tasks →
R9 | 2026-06-15 | 3a61950 | English/Arabic UI language switcher | Released | Sprint 1 → | 1 task →

## Tasks
ID | Epic | Task | Details | Area | Pts | Status | Sprint | Release
CS-1 | Agentic Core | Orchestrator agent + Claude tool-use loop | Multi-step orchestrator that plans, calls tools and assembles the deliverable; runs on Claude Opus. | BE | 8 | Done | Sprint 1 | R1
CS-2 | Agentic Core | Governed tools (RAG + brand) | retrieve_context (pgvector RAG over HUMAIN content) and get_brand_guidelines — read-only and scoped. | BE | 5 | Done | Sprint 1 | R1
CS-3 | Agentic Core | Specialist agents | Drafting, localization (EN/AR), brand-guardian, SEO, editorial, research — delegated focused sub-tasks. | BE | 5 | Done | Sprint 1 | R1
CS-4 | Agentic Core | Per-run audit logging | Every agent run written to the audit log (user=agent-orchestrator) for full traceability. | BE | 2 | Done | Sprint 1 | R1
CS-5 | Conversational Chat & UX | Streaming chat endpoint (SSE) | /studio/chat streams tokens live for a Claude-style response. | BE | 5 | Done | Sprint 1 | R1
CS-6 | Conversational Chat & UX | Converse-then-produce | Asks one clarifying question when the request is ambiguous; otherwise produces. | BE | 3 | Done | Sprint 1 | R1
CS-7 | Conversational Chat & UX | Rich Markdown rendering | Replies render as formatted rich text (headings, lists, tables) — not raw markdown. | FE | 3 | Done | Sprint 1 | R2
CS-11 | Build-Anything | build_site | Builds a complete responsive site, rendered live in-chat with Open/Download. | BE/FE | 5 | Done | Sprint 1 | R2
CS-10 | Conversational Chat & UX | Intent routing + recommendations | Agent decides what to build and proactively suggests next steps. | BE | 5 | Done | Sprint 1 | R3
CS-12 | Build-Anything | build_content | Editable content card (title, body, tags) the user can edit, copy or download. | BE/FE | 5 | Done | Sprint 1 | R3
CS-13 | Build-Anything | Publish-to-module | Markdown→Lexical conversion; publishes a draft to a chosen CMS module for review. | BE/FE | 5 | Done | Sprint 1 | R3
CS-18 | Brand Studio | Recommend→view→verify→publish flow | AI recommends a full guideline; user reviews/edits, then publishes or downloads. | FE/BE | 5 | Done | Sprint 1 | R4
CS-19 | Brand Studio | Active Brand governance | Published active brand (isActive) steers all agent generations. | BE | 3 | Done | Sprint 1 | R4
CS-20 | Design System | Prompt-driven theme | Describe a look; agent generates a full theme with live preview and apply. | BE/FE | 5 | Done | Sprint 1 | R5
CS-8 | Conversational Chat & UX | Natural messages + action row | Replies as natural in-thread messages with Copy/Retry; no framed cards. | FE | 3 | Done | Sprint 1 | R6
CS-9 | Conversational Chat & UX | Focused chat view | Composer drops below the thread and landing rails hide once a conversation starts. | FE | 3 | Done | Sprint 1 | R6
CS-14 | Build-Anything | build_video | Production-ready script/storyboard with a one-click render control. | BE/FE | 5 | Done | Sprint 1 | R6
CS-15 | Build-Anything | build_image | Generates a real image via Replicate/Flux, shown inline. | BE/FE | 5 | Done | Sprint 1 | R6
CS-16 | Build-Anything | build_brand | Verifiable brand guideline card to publish (active brand) or download. | BE/FE | 3 | Done | Sprint 1 | R6
CS-17 | Build-Anything | build_theme | Generates a theme (palette/font/radius) with live swatches and Apply. | BE/FE | 3 | Done | Sprint 1 | R6
CS-23 | Platform / Cost / Infra | Render pipeline | Replicate image/video render service + Studio proxy routes + graceful states. | BE | 3 | Done | Sprint 1 | R6
CS-22 | Platform / Cost / Infra | Cost optimization | Sub-agents/generation on Haiku, orchestrator on Opus — ~5–10x cheaper. | BE | 3 | Done | Sprint 1 | R7
CS-25 | Documentation | Product Requirements Document | Customer PRD with architecture/integration diagrams and product snapshots. | DOC | 3 | Done | Sprint 1 | R8
CS-26 | Documentation | UI/UX and User Journeys | UI/UX and per-feature user journeys with real screenshots. | DOC | 3 | Done | Sprint 1 | R8
CS-27 | Documentation | High-Level Architecture | Context, agent core, sequence, integration and deployment diagrams. | DOC | 3 | Done | Sprint 1 | R8
CS-28 | Documentation | Combined Master Deck | All three documents in one deck — single cover + part dividers. | DOC | 1 | Done | Sprint 1 | R8
CS-29 | Documentation | Build pipeline + repo commit | Branded PDF pipeline + collateral committed to docs/sales (PR #1). | DOC/INF | 2 | Done | Sprint 1 | R8
CS-21 | Bilingual UI | EN/Arabic language switch | Sidebar toggle flips the whole UI to Arabic RTL and back; choice persists. | FE | 5 | Done | Sprint 1 | R9
CS-24 | Platform / Cost / Infra | Deploy + verification cycles | 9 live releases, each built, deployed and verified end-to-end. | INF | 5 | Done | Sprint 1 | R1–R9